City of Toronto

Long-Term Care Homes & Services

2024 Capital Maintenance Plan

Castleview Wychwood Towers

MLTC Review Submission

December, 2024

Fanel Hududui

LTC Home Supervisor,

Supervisor Facility & Mechanical Services (SFMS),

Castleview Wychwood Towers

City of Toronto Senior Services & Long Term Care

351 Christie Street

Toronto, ON, M6G 3C3
416-392-5815
fanel.hududui@toronto.ca

Table of Contents

- Project Summary

  - Maintenance Projects Overview

  - Interior Upgrades– Detailed Description

- Operational Plan

- Overview of Project

- Administration

- Communication

- General Safety Measures

- Emergency Plan / Life Safety Plan

- Resident Home Areas

- Food Service

- Noise Factors

- After Hours Work

- Laundry Services

- Waste Disposal

- Staff Work Space

- Summary

Project Summary

- Maintenance Projects Overview

Castleview Wychwood Towers, located in Toronto, provides individualized care to each of its 456 residents within a safe and friendly environment that respects, supports and enables people to be as independent as possible within an environment that respects the dignity, self-esteem and rights of residents and clients.

Work is to begin following Ministry approval of the plans and completion of the City of Toronto tendering process. From the time the contract has been awarded it is anticipated that the project would take approximately 7 months.

- Project Description

The scope of work for this project includes:

      - Installation of new one-way-driving controlled access gate system for the Entry & Exit of the property;

      - Renovation of the ground floor Reception (Rm 1/030A), and 3rd Washroom Cores (East and West). The renovation includes; new millwork, new doors & door hardware, new security shutter, new ACT & GWB ceilings, new interior partitions, new floor finish, new lighting, new and modified plumbing & HVAC.

The interior  renovation will be done in three phases to minimize resident disruption. Hoarding, dust control, and safety barriers will be installed ensure residents safety.

The work area will be inspected by the Home’s Supervisor Facility & Mechanical Service (hereinafter “SFMS”), or delegate to ensure safety and a satisfactory level of cleanliness.

OPERATIONAL PLAN

- Overview of Project

Phasing

The project will be done in three phases to minimize resident disruption. The phasing has been designed to allow and maintain residents autonomous washroom, showering and bathing access. As one portion of the washroom core is under construction, the residents have free access to the other two portions.

All work within this project will be comprehensively scheduled with the Home prior to start-up on site. This includes start and end dates for each phase, specific tasks, and contingency plans for potential delays. Contractors will be required to adhere to this schedule for the durations of the work. No work shall be left in an unfinished state at days end. All fire alarms turned off during working hours will be completely operational at the end of each day’s work.

Permits/ Approvals

This project will require building permits. All drawings will be submitted to authorities for approval prior to the commencement of work.

Hours of Work

The following work will take place during regular working hours as defined in the Project Specification and as determined by the SFMS, 8.00 a.m. to 5.00 pm. and effective sequencing of work must be considered for any unanticipated event.

Anticipated Timelines
It is anticipated that this project will begin on or around July 2025, and be completed by February  2026.

Special Considerations

Contractor shall coordinate area of work with the Home.

Resident Services Manager will plan and oversee all resident activities.  If required, Resident activities will be relocated to a suitable location depending on daily scheduled work.

Construction and demolition in the washroom cores shall be phased and coordinated to minimize the impact on general day to day function of the home.

Environmentally friendly, low odour glue will be exclusively used to protect the health of residents and staff.

- Administration

The home is administered by Donna Lee who will be assisted during this project by the home's staff, particularly Fanel Hududui, SFMS. The architect for the project is Montgomery Sisam Architects Inc. The City of Toronto’s Head Office Project Manager will also manage the Owners responsibilities.

In order to facilitate effective and timely communication the following protocols will be in-place:

- Bi-weekly check-in meetings with home, divisional project lead, project architects and contractors on project start.

- Weekly check-in meetings with home, divisional project lead, project architects and contractors when site work commences.

- Administrative rounds with the SFMS and union co-chair of the OH&S Committee as required.

- Communication

Before construction begins, a start-up meeting will be held with the contractor and home staff, outlining the requirements imposed on contractors working in a Long-Term Care environment, and protocols that the contractor will be expected to follow. All issues with respect to both resident and staff safety will be identified with staff involvement and will be communicated through both informal and formal meetings.

- The Residents' Council as well as residents and families will be kept informed.

- All staff will be informed via departmental meetings, memos and newsletter.

- A formal communication plan will be developed for the purpose of reporting issues on a timely basis to enable prompt follow up.

- The Administrator or delegate will notify the Ministry of Health & Long-Term Care Regional Office when work is about to begin.

- General Safety Measures

Name of persons assigned to monitor safety: Fanel Hududui, SFMS.

All areas of work will be separated from building users and visitors using barricades and/or hording as required as to the satisfaction of the SFMS and the Architect.

Each area will be cleaned of debris and construction material frequently during each day and through cleaning at shift end.

- Barriers / Tool and Equipment Storage

The contractor must provide temporary measures to ensure all work areas, for all projects, are secure from residents between all working areas and resident spaces. Dust protection must be incorporated to protect residents and resident spaces from dust exposure.

Tools and equipment must be not be left in areas accessible to residents and must be locked in a secure location when unattended. All tools and equipment shall be stored in a secured location as coordinated with the SFMS.

- Alarms

All door alarms, fire alarms and nurse call devices will operate normally in all areas of the home during the renovation period. Should it be necessary to temporarily bypass a fire zone, a manual fire watch will be implemented.  All fire zones will be restored to full operation at the end of each construction day.

- Water Shutoff

It is not anticipated that any building water shutoffs will be required for this project – only localized freezing.  If water shutoffs affecting residents are required, the contractor will need to provide 48 hours’ notice and get Home’s approval.  Any required water shutoffs affecting residents will only be permitted during the day and must be minimized as much as possible.

- Housekeeping / Cleanliness

The contractor shall keep all construction areas clean of construction debris and waste throughout the day.

Housekeeping routines will be adjusted to maintain an acceptable level of cleanliness. Housekeeping hours will be adjusted, if required, to keep up with the increased demand.

- Transporting Construction Materials

Construction deliveries will be delivered to specific area as coordinated with the SFMS. All materials that are to be transported throughout the building shall be transported by routes as informed by the SFMS. If required to transport goods and equipment to floor levels not accessible from grade level, the Contractor shall use a dedicated elevator and must coordinate with the home timelines for elevator use to cause minimal disturbances to the home.

- Dust Control

The Contractor shall ensure all dust control strategies are used to prevent the spread of dust and contaminants to resident areas. Examples of such strategies, but not limited to; are sealed hoarding, air quality checks and monitoring. The contractor shall coordinate the dust control strategy with the SFMS prior to construction.

- Emergency Plan / Life Safety Plan

Although work on this project should not cause a disruption to essential services, if such a disruption were to occur the home Emergency Measures Plan would be put into effect. The plan has measures that compensate for loss of electricity or natural gas supply. In case of urgent issues related to the renovation, the plan includes to up-to-date access to emergency contact information. In order to ensure the smooth implementation of the Emergency Measures Plan, the Administrator and the SFMS will review the plan and become comfortable with it before work commences on this project.

- Resident Home Areas (RHA)

It is anticipated that there will be minimal impacts on resident home areas. Any impact on areas with residents (if required) will be planned and overseen by the Resident Services Manager. Resident activities will be relocated to a suitable location on the unit depending on daily scheduled work.

- Food Service

There will be no impact to food services.

Delivery of food and any other supplies required to provide care to the residents will not be affected due to this project.

- Noise Factors

Construction will take place during the normal business hours of 8:00 a.m. and 5:00 p.m.  Should there be any significant noise levels required during construction, the contractor shall notify the Home a minimum of 48 hours in advance of the work. The contractor shall coordinate with the SFMS the implementation of quiet hours during peak times for resident activities (such as dining), to further minimize noise disruption. Noise levels will be monitored by the SFMS and Home Staff.

- After Hours Work

It is anticipated there will be minimal if any afterhours work required. The timing of any required work will be coordinated to minimize the impact to residents. All afterhours work shall be at the approval of the SFMS.

- Laundry Services

There will be no impact to Laundry Services.

- Waste Disposal

Contractor to put a waste bin within the loading area of Long-Term Care Home – location to be confirmed by SFMS. Contractor should erect a signage to make sure no mixing on construction and home waste.

- Staff Work Space

It is anticipated that there will be minimal impact on Staff Work Space. Any works related to staff work spaces will be scheduled and coordinated with SFMS to ensure no staff will be affected.

- Summary

The work outlined in this operational plan will require co-ordination and communication between the Contractor and the Home to ensure the planned improvements are achieved with minimal impact to residents.

When preparing this Operational Plan an emphasis was placed on the resident and staff's comfort and safety. This plan works to minimize impact on the daily lives of the people living and working at each Home by holding contractors to their schedules and maintaining clear lines of communication between all staff members, residents and families.